## Sheet1
Task | Phase | Person | Effort | ETA | Comments
Add Certificates (D&D) | 1 | Eli | 1d | 2013-12-08
Remove Certificates | 1 | Guy \ Rotem
Add Content (D&D) | 1 | Eli | 1d | 2013-12-08
Remove Content | 1 | Alon \ Rotem
Change Content Sequence (D&D) | 1 | Eli | 1d | 2013-12-08
Display Notes | 1 | Alon
Add \ Edit \ Disable Notes | 1 | Alon
Content Execution | 1 | Guy |  |  | Also requires a control from Eli, to be delivered by Dec-8
Contents tab on Projects | 1 | Rotem
Clone Projects (Regular) | 1 | Rotem
Update version file path | 1 | Rotem |  |  | I think it requires the control mentioned above
Security | 1 | All |  |  | This is done; make sure you use it like I do
QA - Functionality | 1
QA - Run on XP \ Win7 \ Win8 | 1
QA - Performance | 1
Re-Sequence Folders (not alphabetically) | 2 | Eli
Search on Content Name and Notes | 2 | Eli
Clone Projects (Related) | 2 | Rotem
Modify Related Project | 2 | Rotem
Show versions on the TreeView | 2 | Rotem